## Sheet1
Sprint | Feature Set / Requirements ID | Topic | User Story | Task # | Task | Priorities | Assigned To | Start Date | End Date | Hours(Task Based)Estimate the testing+development-Technical Panel | Story Point(Bussiness Value/Complexity)Estimate how much we can deliver in a sprint+total efford with its task with its risk dependencies and other Factors(Pro+Scrum) | Status | Short Description of Feature Set/ Feature | Dependency of Feature Set/ Feature | Feature Owner | Feature Complexity | Business Priority | Feature Type | Remarks
1.1 | #1 | Application Kickstart | As a User I want to display a Login page which will redirect me to Welcome page. | Task 1 | Create a jsp page with Login link | critical | Shubham Srivastava |  |  | 2 | [6 empty] | critical | New Requirement
2.1 |  | Initial Selection | As a user when I arrive on the welcome page,I should get the option of both login and registration. | Task 2 | Create a jsp page with Login and Registration Link | critical | Saurabh Gidwani |  |  | 2 | [6 empty] | critical | New Requirement
2.2 |  | Customer Login | As a user if I enter valid credentials I should be able to Login successfully | Task 3 | Display a welcome JSP page | critical | Shivam Goel |  |  | 3 | [6 empty] | critical | New Requirement
|  | Customer Registration | As a user when I click on "Register", I should be provided with an option to choose for Doctor/Customer / Admin Registration | Task 4 | Create a JSP registration form that accepts respective attribute | critical | Vinayak Gupta |  |  | 3 | [6 empty] | critical | New Requirement
|  | Customer Registration | As a Customer/Doctor/Admin if I leave a field it should mark the field as red and restrict the user from registering | Task 5 | Add JS functionality to mark the unfilled field as red | critical | Shubham Srivastava |  |  | 2 | [6 empty] | critical | New Requirement
|  | Credential Authentication | As a customer on succesful registration I should be redirected to login page and should be able to login with submitted credentials | Task 6 | Match the entered credentials from the DB entries | High | Saurabh Gidwani |  |  | 2 | [6 empty] | High | New Requirement
10.1 |  | View for Customer | As a customer on clicking View Medicare services, the page should list all the Medicare Services,Doctors available | Task 7 | Create a JSP page containing View option with drop down containing followin three options | Critical | Shivam Goel |  |  | 3 | [6 empty] | Critical | New Requirement
10.2 |  | View/Medicare Services | As a customer on choosing Medicare Services I should be redirected to a page containing all available services and their ID | Task 8 | Create a JSP page containing list of Medicare Services and their ID | Critical | Vinayak Gupta |  |  | 2 | [6 empty] | Critical | New Requirement
10.3 |  | View/Medicare Services | As a customer on Clicking the Medicare ID, it should display all the details of the Medicare services | Task 9 | Attach a link to Service ID that redirects to the full Service details. | Critical | Shubham Srivastava |  |  | 3 | [6 empty] | Critical | New Requirement
10.4 |  | View medicare services/doctor | As a customer on clicking Doctors I should be redirected to a page containing all available Doctors and their ID |  | Create a JSP page containing list of Available Doctors and their ID | Critical | Saurabh Gidwani |  |  | 2 | [6 empty] | Critical | New Requirement
10.5 |  | View/Medicare Services | As a customer on Clicking the Doctor's ID, it should display all the details about the Doctor |  | Attach a link to Doctor's ID that redirects to the full Doctor's details. | Critical | Shivam Goel |  |  | 3 | [6 empty] | Critical | New Requirement
10.6 |  | Raise checkup request | As a Customer I can be able to raise the checkup request for my treatment |  |  | critical |  |  |  | 2 | [6 empty] | Critical | New Requirement
10.7 |  | view test result | As a Customer I am able to view my updated Test results |  | Attach a link to Doctor's ID that redirects to the full Agent's details. | Critical | Shubham Srivastava |  |  | 3 | [6 empty] | Critical | New Requirement
|  | customer log off | As a customer after completion of my work I should have an option of logout. |  |  | critical
|  | Doctor Registration | As a doctor i can approve / reject the customer Request. |  |  | critical
Shubham Srivastava
Saurabh Gidwani
Shivam Goel
Vinayak Gupta
S
M
L
XL