## Sheet1
Sprint | Feature Set / Requirements ID | Topic | User Story | Task # | Task | Priorities | Assigned To | Start Date | End Date | Hours(Task Based)Estimate the testing+development-Technical Panel | Story Point(Bussiness Value/Complexity)Estimate how much we can deliver in a sprint+total efford with its task with its risk dependencies and other Factors(Pro+Scrum) | Status | Short Description of Feature Set/ Feature | Dependency of Feature Set/ Feature | Feature Owner | Feature Complexity | Business Priority | Feature Type | Remarks
#1 |  | Initial selection | Initially the screen should display the option for Login and Registration for Admin,Doctor and Customer | Task | Create a login JSP which is integrated with the spring security . | critical |  |  |  | 2 |  | Done |  |  |  |  | critical | New Requirement
|  |  |  | Task | On clicking registration link it will be redirected to the registration forms of Customer,Admin and doctor | [6 empty] | Done
|  |  |  | Task | we have created a navigation bar which will redirect to the different registration forms. | [6 empty] | Done
|  | Customer Registration | As a customer when I clicks on the registration link, it should re-direct to registration form. | Task | Create a JSP for customer registration which will have all the necessary fields. | critical |  |  |  | 2 |  | Done |  |  |  |  | critical | New Requirement
On clicking Register button the form validates using JS .
After validation data is populated into the corresponding database.
|  | Customer Registration | As a customer on Clicking 'Submit' should validate the datatype constraints for each field | Task | On submit JS validation is triggered | critical |  |  |  | 3 |  | Done |  |  |  |  | critical | New Requirement
|  | Customer Registration | As a customer if I am failing to provide information on the mandatory fields be provided with an alert message - 'Please update the highlighted mandatory field(s).' Also, highlight the missed out field in red | Task | Add JS functionality to mark the unfilled field as red | critical |  |  |  | 2 |  | Done |  |  |  |  | critical | New Requirement
|  | Customer Registration | As a Admin i should be able to view the New Customers for registration | Task | Create a JSP page which retrives all the customer present in the database . | Critical |  |  |  | 2 |  | Done |  |  |  |  | Critical | New Requirement
|  | Credential Authentication | A registered Customer - is able click 'Login' link, after keying in 'Customer ID' & 'Password' field and get his credentials authenticated with the existing database entry. | Task | On entering 'Customer ID' & 'Password' the connection with the database is established | critical |  |  |  | 2 |  | Done |  |  |  |  | Critical | New Requirement
|  |  |  | Task | Now the 'Customer ID' will be verified from the database if it exists then the encrypted password is and the verified from the existing password in the database.
|  |  |  | Task | On successful validation it would be redirected to the respective Dashboard
|  | Doctor Registration | As a doctor when I click on the registration link, it should re-direct to registration form. | Task |  | Critical |  |  |  | 3 |  | Done |  |  |  |  | Critical | New Requirement
#2 |  | Doctor Registration | As a doctor on 'Submit' should validate the datatype constraints for each field | Task |  | critical | [5 empty] | Done
|  | Doctor Registration | As a doctor failing to provide information on the mandatory fields be provided with an alert message - 'Please update the highlighted mandatory field(s).' Also, highlight the missed out field in red | Task |  | Medium | [5 empty] | Done
|  | Doctor Registration | As a admin i should be able to view the New Doctors for registration | Task |  | critical | [5 empty] | Done
|  | Admin Registration | As a admin when I click on the registration link, it should re-direct to registration form. | Task |  | critical | [5 empty] | Done
|  | Admin Registration | As a admin i needs to fill some of the basic attributes/fields as mentioned below in requirement: First Name, Last Name, Age, Gender, Contact Number, admin Id, Password | Task |  | critical | [5 empty] | Done
|  | Admin Registration | As a admin on 'Submit' should validate the datatype constraints for each field | Task |  | critical | [5 empty] | Done
|  | Admin Registration | As a admin if I am failing to provide information on the mandatory fields be provided with an alert message - 'Please update the highlighted mandatory field(s).' Also, highlight the missed out field in red | Task |  | Medium | [5 empty] | Done
|  | Update Medicare Service Details | As a doctor i should be able to update the mandatory fields of the Medicare Service | Task# | Create a JSP form displaying previous values of fields Name,Amount and Description | critical | [5 empty] | Done
|  |  |  | Task | Send the updated details to Medical service controller class through model attribute service. | [6 empty] | Done
|  |  |  | Task | Save the model attribute in object of Medical service class and pass it to DAO layer through Service layer for update and save | [6 empty] | Done
|  |  |  | Task | Display a message through Javascript on successful submisson of Medical Service details. | [6 empty] | Done
Display/redirect to the JSP page containing all the updated Medical Services
#3 |  | View Medicare Service/ Doctor / Agent details | As a customer on Clicking the View button corresponding Medicare ID, it should list all the details of the Medicare services | Task | Create a JSP page listing all the Medicare Services and a view button corresponding to them | critical | [5 empty] | Done
|  |  |  | Task | Create a function in controller layer that will accept the Medicare Service ID provided by view button.
|  |  |  | Task | Function will call a method in service and DAO layer that accepts ID as parameter and return the Medicare Service object, which is then passed as model attribute to the JSP.
|  |  |  | Task | Create a JSP displaying details of Medicare Services in that object.
|  | View Medicare Service/ Doctor / Agent details | As a customer on clicking View Doctor, the page should list all the doctors available | Task | On clicking view doctor a function returning list of all the doctors is called | critical | [5 empty] | Done | S
|  |  |  | Task | The return list of doctors is added as a attribute and is passed to the JSP.
|  |  |  | Task | Create a JSP displaying list of all available Doctors.
|  | View Medicare Service/ Doctor / Agent details | By Clicking the Doctor Id, it should display all the details of the doctor | Task | Create a function in controller layer that will accept the Doctor ID provided by view button.
Function will call a method in service and DAO layer that accepts ID as parameter and return theDoctor object, which is then passed as model attribute to the JSP.
[5 empty] | Create a JSP displaying details of Doctor in that object. | critical | [5 empty] | Done | M
|  | Raise Checkup request | As a customer when I Click on Raise Checkup request link, it should redirect to the Request creation page | Task |  | Critical | [5 empty] | Done
|  | Raise Checkup request | As a customer i should be able to fill in the necessary fields, select date, doctor and Medicare service and submit the request | Task | [7 empty] | Done
|  | Raise Checkup request | As a doctor i should be able to view the Checkup request and approve it | Task |  | critical | [5 empty] | Done
|  | Update Test results | As a doctor on clicking the Checkup request ID, Doctor should have the option to update the test results | Task |  | critical | [5 empty] | Done
|  | View test results | As a customer on clicking the Checkup request ID, Doctor / consumer should be able to view the test results | Task |  | Critical | [5 empty] | Done
|  | Admin/Customer/Doctor log off | Option to log off from the system. | Task | [7 empty] | Done
Shubham Srivastava
Saurabh Gidwani
Shivam Goel
Vinayak Gupta